## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 |  | US-01 | Generate synthetic healthcare data using Faker | MUST HAVE | None | Neha Kumari | 3- Completed
Sprint 1 |  | US-02 | Prepare patient and hospital data for analysis | MUST HAVE | US-01 | Neha Kumari | 3- Completed
Sprint 1 |  | US-03 | Check missing values and duplicate records | MUST HAVE | US-02 | Sayali Devkar | 3- Completed
Sprint 1 |  | US-04 | Select useful columns for analysis | MUST HAVE | US-02 | Sayali Devkar | 3- Completed
Sprint 1 |  | US-05 | Create the final dataset for analysis | MUST HAVE | US-03, US-04 | Sayali Devkar | 3- Completed
Sprint 1 |  | US-06 | Perform basic EDA on the dataset | MUST HAVE | US-05 | Sayali Devkar | 3- Completed
Sprint 2 |  | US-07 | Analyze patient admission and discharge trends | MUST HAVE | US-05, US-06 | Vedika Pandey | 3- Completed
Sprint 2 |  | US-08 | Analyze treatment demand by department | MUST HAVE | US-05, US-06 | Kancharla Jahnavi | 3- Completed
Sprint 2 |  | US-09 | Analyze departmental workload | MUST HAVE | US-05, US-06 | Kancharla Jahnavi | 3- Completed
Sprint 2 |  | US-10 | Create KPIs for patient flow and services | MUST HAVE | US-07, US-08 | Manoj | 3- Completed
Sprint 2 |  | US-11 | Create charts for patient and treatment trends | MUST HAVE | US-05, US-06 | Manoj | 3- Completed
Sprint 2 |  | US-12 | Identify high-demand areas and bottlenecks | SHOULD HAVE | US-05, US-06 | Neha Deshmukh | 3- Completed
Sprint 3 |  | US-13 | Calculate bed occupancy and availability | MUST HAVE | US-11, US-12 | Vedika Pandey | 3- Completed
Sprint 3 |  | US-14 | Analyze doctors and staff workload | MUST HAVE | US-13 | Vedika Pandey | 3- Completed
Sprint 3 |  | US-15 | Analyze hospital resource utilization | MUST HAVE | US-13 | Devshree Pavle | 3- Completed
Sprint 3 |  | US-16 | Create KPIs for resource utilization | MUST HAVE | US-13 | Devshree Pavle | 3- Completed
Sprint 3 |  | US-17 | Create charts for resource and workforce analysis | MUST HAVE | US-15, US-16 | Kancharla Jahnavi | 3- Completed
Sprint 3 |  | US-18 | Identify areas with high resource usage | SHOULD HAVE | US-14, US-17 | Neha Kumari | 3- Completed
Sprint 4 |  | US-19 | Create interactive Power BI dashboards | MUST HAVE | US-18 | Neha Deshmukh | 3- Completed
Sprint 4 |  | US-20 | Add filters and slicers to the dashboards | MUST HAVE | US-19 | Manoj | 3- Completed
Sprint 4 |  | US-21 | Analyze patients and services by location | SHOULD HAVE | US-05, US-06 | Vedika Pandey | 3- Completed
Sprint 4 |  | US-22 | Add insights from the analysis | MUST HAVE | US-10, US-18, US-21 | Devshree Pavle | 3- Completed
Sprint 4 |  | US-23 | Test and validate the dashboard | MUST HAVE | US-19, US-22 | Devashree Pavle | 3- Completed
Sprint 4 |  | US-24 | Document the project and update GitHub | MUST HAVE | US-23 | Neha Kumari | 3- Completed
Sprint 4 |  | US-25 | Deploy and present the final dashboard | MUST HAVE | US-23, US-24 | Neha Deshmukh | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 50 | 10 | 8 | 9 | 9 | 9 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-01 | T-01 | Identify and collect relevant healthcare datasets | 2026-07-22 | 2026-07-24 | Neha Kumari | Data Collection | completed | 6 | Day 1: 6
US- 01 | T-02 | Review dataset structure, columns and data quality | 2026-07-22 | 2026-07-24 | Neha kumari | Data Analysis | completed | 4 | Day 1: 4
US-02 | T-03 | Load raw datasets using Pandas | 2026-07-23 | 2026-07-24 | Devashree Pavle | Data Processing | completed | 3 | Day 2: 3
US-02 | T-04 | Handle missing values and duplicates | 2026-07-23 | 2026-07-24 | Devashree Pavle | Data Cleaning | completed | 5 | Day 2: 5
US-03 | T-05 | Standardize dates, categorical values and data types | 2026-07-23 | 2026-07-24 | Sayali Devkar | Data Cleaning | completed | 5 | Day 3: 5
US-04 | T-06 | Select relevant columns for project KPIs | 2026-07-23 | 2026-07-24 | Sayali Devkar | Data Analysis | completed | 4 | Day 3: 4
US-05 | T-07 | Merge related datasets where required | 2026-07-23 | 2026-07-24 | Vedika Pandey | Data Integration | completed | 6 | Day 4: 6
US-05 | T-08 | Export cleaned/processed dataset | 2026-07-23 | 2026-07-24 | Vedika Pandey | Data Processing | completed | 3 | Day 4: 3
US-06 | T-09 | Define Total Patients, Admissions, Discharges and LOS KPIs | 2026-07-23 | 2026-07-24 | Manoj | KPI Definition | completed | 5 | Day 5: 5
US-06 | T-10 | Validate KPI calculations against source data | 2026-07-23 | 2026-07-24 | Manoj | Validation | completed | 4 | Day 5: 4
US-05 | T-11 | Create project repository and folder structure | 2026-07-23 | 2026-07-24 | Neha Deshmukh | GitHub | completed | 2 | Day 6: 2
US-05 | T-12 | Update README with data pipeline and setup instructions | 2026-07-23 | 2026-07-24 | Neha Deshmukh | Documentation | completed | 3

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Difficulty in preparing the healthcare dataset | Generated synthetic data using Faker
Sprint 1 | Day 2 | Missing values and duplicate records | Cleaned and validated the dataset
Sprint 1 | Day 3 | Some columns were not useful for analysis | Selected relevant columns
Sprint 2 | Day 1 | Difficulty in identifying useful KPIs | Discussed requirements and finalized KPIs
Sprint 2 | Day 2 | Charts were not giving clear insights | Changed chart types and improved visualizations
Sprint 3 | Day 1 | Difficulty in calculating resource utilization | Created and validated required calculations
Sprint 3 | Day 2 | Dashboard values needed validation | Compared dashboard results with source data
Sprint 4 | Day 1 | Final dashboard required testing before presentation | Tested the complete dashboard and fixed issues
Sprint 4 | Day 2 | Preparing the final demo and presentation | Finalized presentation and divided demo responsibilities

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-07-24 | 2026-07-31 | Neha Kumari | Start generating data using Faker | Stop using unclean data | Continue data preparation | Synthetic data generated
2 | Sprint 1 | 2026-08-01 | 2026-08-03 | Neha Deshmukh | Start checking data quality | Stop ignoring duplicate records | Continue data cleaning | Missing values and duplicates checked
3 | Sprint 2 | 2026-08-03 | 2026-08-07 | Sayali Devkar | Start performing EDA | Stop creating visuals without analysisContinue exploring data patterns | Continue exploring data patterns | EDA complete
4 | Sprint 2 | 2026-08-09 | 2026-08-17 | Kancharla Janahvi | Start creating healthcare KPIs | Stop using unnecessary metrics | Continue KPI analysis | KPIs prepared
5 | Sprint 3 | 2026-08-17 | 2026-08-25 | Devshree Pavle | Start analyzing resource utilization | Stop manual calculations | Continue bed and workforce analysis | Resource KPIs calculated
6 | Sprint 3 | 2026-08-27 | 2026-09-08 | Vedika Pandey | Start validating dashboard results | Stop using static values | Continue Power BI development | Dashboard checked | 0
7 | Sprint 4 | 2026-09-11 | 2026-09-16 | Manoj | Start documenting project work | Stop last-minute documentation | Continue team coordination | Documentation updated