## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Project Team | 2026-09-11 | DEF-001 ¦ Patient Flow ¦ Monthly admission count was not updating correctly after applying date filter | Sprint 2 | Neha Kumari | Logical | Corrected the date filtering logic to ensure monthly admission counts update correctly. | 2026-09-16 | Closed | Severity: High ¦ Priority: High
2 | Project Team | 2026-09-11 | DEF-002 ¦ Patient Flow ¦ Dashboard showed incorrect total admissions for filtered department | Sprint 2 | Sayali Devkar | Logical | Fixed the department filter calculation to display the correct total admissions. | 2026-09-16 | Closed | Severity: Medium ¦ Priority: High
3 | Project Team | 2026-09-11 | DEF-003 ¦ Resource Utilization ¦ Bed occupancy percentage was calculated incorrectly | Sprint 3 | Neha Deshmukh | Logical | Corrected the bed occupancy calculation formula. | 2026-09-16 | Closed | Severity: High ¦ Priority: High
4 | Project Team | 2026-09-11 | DEF-004 ¦ Resource Utilization ¦ Available bed count did not match total beds minus occupied beds | Sprint 3 | Kancharla Jahnavi | Logical | Updated the KPI calculation to correctly calculate available beds as total beds minus occupied beds. | 2026-09-16 | Closed | Severity: Medium ¦ Priority: High
5 | Project Team | 2026-09-11 | DEF-005 ¦ Geographic Analysis ¦ Some patient locations were missing from the map | Sprint 4 | Devashree Pavle | Data | Cleaned and standardized patient location values to ensure all valid locations are displaye on the map. | 2026-09-16 | Closed | Severity: Medium ¦ Priority: Medium
6 | Project Team | 2026-09-11 | DEF-006 ¦ Dashboard ¦ Charts were not refreshing correctly after changing filters | Sprint 4 | Vedika | Functional | Fixed the filter and data refresh logic to ensure charts update correctly when filters are changed. | 2026-09-16 | Closed | Severity: High ¦ Priority: High
7 | Project Team | 2026-09-11 | DEF-007 ¦ Dashboard ¦ Dashboard displayed empty charts when no records matched filters | Sprint 4 | Manoj | Functional | Added empty-data handling to display an appropriate message when no records match the selected filters. | 2026-09-16 | Closed | Severity: Low ¦ Priority: Medium
8 | Project Team | 2026-09-11 | DEF-008 ¦ Dashboard ¦ KPI values differed between Python calculation and dashboard | Sprint 4 | Devashree Pavle | Logical | Validated and corrected KPI logic to ensure dashboard values match Python calculations. | 2026-09-16 | Closed | Severity: High ¦ Priority: High
9 | Project Team | 2026-09-11 | DEF-009 ¦ UI ¦ Long chart labels were overlapping on smaller screens | Sprint 4 | Sayali Devkar | UI | Adjusted chart layout and label formatting to prevent overlapping labels on smaller screens. | 2026-09-16 | Closed | Severity: Low ¦ Priority: Low
10 | Project Team | 2026-09-11 | DEF-010 ¦ Deployment ¦ Application failed to load correctly after deployment | Sprint 4 | Neha Deshmukh | Deployment | Fixed deployment configuration and required dependencies to ensure the application loads correctly after deployment. | 2026-09-16 | Closed | Severity: High ¦ Priority: High

## Sheet2
Logical
User Interface
Maintainability
Standards
Others